## Sheet 1 - Table 1
Table 1
S.No. | S.No. User Story index | Task | Date introduced | Date considered for implementation | Date completed | Developer responsible for | Current Status
1 | 1 | Develop GUI portion for block view | 2017-01-28 | 2017-01-28 | 2017-01-28 | Anxin Liu | Completed
2 | 1 | Develop Code for block view | 2017-01-28 | 2017-01-28 | 2017-01-29 | Guanzhong Qian | Completed
3 | 1 | Test code for block view | 2017-01-28 | 2017-01-28 | 2017-01-29 | Zhihao Yuan | Completed
4 | 7 | Develop GUI portion for Set the size of Rectangular | 2017-01-28 | 2017-01-30 | 2017-01-30 | Anxin Liu | Completed
5 | 7 | Develop Code for Set the size of Rectangular | 2017-01-28 | 2017-01-30 | 2017-01-31 | Zhihao Yuan | Completed
6 | 7 | Test code for Set the size of Rectangular | 2017-01-28 | 2017-01-30 | 2017-01-31 | Guanzhong Qian | Completed
7 | 8 | Develop GUI portion for Set agents(position, numbers) | 2017-01-28 | 2017-02-02 | 2017-02-02 | Anxin Liu | Completed
8 | 8 | Develop Code for Set agents(position, numbers) | 2017-01-28 | 2017-02-02 | 2017-02-02 | Guanzhong Qian | Completed | \
9 | 8 | Test code for Set agents(position, numbers) | 2017-01-28 | 2017-02-02 | 2017-02-02 | Zhihao Yuan | Completed
10 | 9 | Develop GUI portion for Set Obstacle(position, numbers) | 2017-01-28 | 2017-02-04 | 2017-02-03 | Anxin Liu | Completed
11 | 9 | Develop Code for Set Obstacle(position, numbers) | 2017-01-28 | 2017-02-04 | 2017-02-04 | Zhihao Yuan | Completed
12 | 9 | Test code for Set Obstacle(position, numbers) | 2017-01-28 | 2017-02-04 | 2017-02-04 | Guanzhong Qian | Completed
13 | 10 | Set up the database | 2017-02-02 | 2017-02-07 | 2017-02-07 | Guanzhong Qian | Completed
14 | 10 | Develop DB access methods | 2017-02-02 | 2017-02-07 | 2017-02-08 | Guanzhong Qian | Completed
15 | 10 | Create Record Class | 2017-02-02 | 2017-02-07 | 2017-02-08 | Zhihao Yuan | Completed
16 | 10 | Unit Test Record Class | 2017-02-02 | 2017-02-08 | 2017-02-09 | Anxin Liu | Completed
17 | 2 | Develop GUI portion for graphical view | 2017-02-02 | 2017-02-09 | 2017-02-10 | Anxin Liu | Completed
20 | 2 | Develop GUI portion for switch between block and graphical views | 2017-02-02 | 2017-02-12 | 2017-02-13 | Guanzhong Qian | Completed
21 | 2 | Develop Code for switch between block and graphical views | 2017-02-02 | 2017-02-12 | 2017-02-13 | Guanzhong Qian | Completed
22 | 2 | Test code for switch between block and graphical views | 2017-02-02 | 2017-02-13 | 2017-02-13 | Anxin Liu | Completed
23 | 3 | Develop GUI portion for Step By Step model | 2017-02-02 | 2017-02-13 | 2017-02-14 | Zhihao Yuan | Completed
24 | 3 | Develop Code for Step By Step model | 2017-02-02 | 2017-02-14 | 2017-02-14 | Zhihao Yuan | Completed
25 | 3 | Test code for Step By Step model | 2017-02-02 | 2017-02-14 | 2017-02-14 | Anxin Liu | Completed
26 | 4 | Develop GUI portion for Run model | 2017-02-02 | 2017-02-14 | 2017-02-15 | Anxin Liu | Completed
27 | 4 | Develop Code for Run model | 2017-02-02 | 2017-02-15 | 2017-02-15 | Zhihao Yuan | Completed
28 | 4 | Test code for Run model | 2017-02-02 | 2017-02-15 | 2017-02-15 | Guanzhong Qian | Completed
29 | 4 | Develop GUI portion for switch between Step By Step model and Run model | 2017-02-02 | 2017-02-15 | 2017-02-16 | Zhihao Yuan | Completed
30 | 4 | Develop Code for switch between Step By Step model and Run model | 2017-02-02 | 2017-02-15 | 2017-02-16 | Zhihao Yuan | Completed
31 | 4 | Test code for switch between Step By Step model and Run model | 2017-02-02 | 2017-02-16 | 2017-02-16 | Guanzhong Qian | Completed
35 | 10 | Develop GUI portion for Observe Record History | 2017-02-02 | 2017-02-17 | 2017-02-18 | Anxin Liu | Completed
36 | 10 | Develop Code for Observe Record History | 2017-02-02 | 2017-02-18 | 2017-02-19 | Anxin Liu | Completed
37 | 10 | Test code for Observe Record History | 2017-02-02 | 2017-02-18 | 2017-02-19 | Zhihao Yuan | Completed
18 | 2 | Develop Code for graphical view | 2017-02-02 | 2017-02-19 |  | Guanzhong Qian | In Progress
19 | 2 | Test code for graphical view | 2017-02-02 | 2017-02-20 |  | Zhihao Yuan | Not determined
38 | 5 | Develop GUI portion for Set Step Number Upper Limit function | 2017-02-02 | 2017-02-21 |  | Zhihao Yuan | Not determined
39 | 5 | Develop Code for Set Step Number Upper Limit function | 2017-02-02 | 2017-02-21 |  | Zhihao Yuan | Not determined
40 | 5 | Test code for Set Step Number Upper Limit function | 2017-02-02 | 2017-02-22 |  | Guanzhong Qian | Not determined
Develop GUI portion for Uploading input file
Develop Code for Uploading input file
Test code for Uploading input file
Develop GUI portion for View record
Develop Code for View record
Test code for View record
Develop Code for execute algorithm
Test code for Execute algorithm
Develop GUI portion for View visualization in graphic view
Develop Code for View visualization in graphic view
Test code for View visualization in graphic view